## ProgressReport
Sno | Date | Planned tasks | Notes | Hours wise progress | Goals accomplished | Follow-ups, if any
1 | 2023-07-18 | 1. Send BNC survey questions to Prof. Quincy and Prof. Jason.(HP) 2. Obtain permission of authorized person at BNC for tomorrow's survey and seek their help. (HP) 3. Send WorkReport, BNC data and list of food banks/pantries to Prof. Quincy and Prof. Jason. (HP) 4. Visit South Corvallis Food Bank, Stone. Soup center which are open today. 5. Check Winnow and other sites for data and methods by which they conduct food analysis. 6. Build a qualtrics survey with help of Prof. Quincy. (HP) |  | 8:00 - 9:00 - task 3. 9:00 - 10:30 - task 1 10:30 - 12:30 - studied FAO website, task 5 12:30 -1: 30 - task 2 1:30 - 5:30 - task 4 | 1. Sent BNC survey questions to Prof. for review. 2. Obtained permission from BNC person for survey and got details. 3. Sent work report, obtained data to Prof. 4. Visited St. VIncent De Paul Food Bank and got contacts of the pantrry owner there. Also, they serve stone soup at 3 sitess and the owner is the same so got that person's contact as well. South Corvallis food bank was closed by the time i reached there. 5. Checked FAO site and the methods they use for data collection and analysis. Additionally - as I was near the first source, i also went to Community Outreach center. | Carry forward followup - 1. Farmers's market follow up. 2. Refine data obtained from BNC - ask BNC about the missing data to complete the excel.
2 | 2023-07-19 | 1. Send Workreport to Prof. 2. Contact St. Vincent De Paul, Stone Soup and Community Outreach center. 3. Visit South Corvallis Food Bank. 4. Contact North Minister Center, Linn benton food share. 5. Attend weekly meetingss |  | 12:00 - 1:00 - task 2 1:00 - 3:00 - task 3 3:00 - 6:00 - task 5 6:00 -8: 30 - task 4 | 1. Sent mails to St. Vincent de Paul, Stone Soup and COI. 2. Visited South Corvallis Food Bank andd got their contact and have emailed them. 3. Also emailed North Ministry food center which is rather a pantry at a church called The Gathering, and Linn benton food share is just a site listing all the other pantries, meal sites. 4. Attended weekly meetings. | Carry forward followup - 1. Farmers's market follow up. 2. Refine data obtained from BNC - ask BNC about the missing data to complete the excel. 3. BNC questions need IRB approval.
3 | 2023-07-24 | 1. Plan and send the next phase of data collection on grocery stores, OSU dining centers and cafes, etc - discuss in the meeting. 2. Visit Oxford house - UHDS center and get contacts of all managers of UHDS. 3. Follow up with all the food pantry/food bank guys. |  |  | 1. Got the list of contact of managers of UHDS. 2. Researched on the Winnow site. |  | (HP) - High Priority
Setting Weekly targets
4 | 24th July Week | 1.Contact Winnow’s clients/customer and Winnow’s Sales people for the data as well as for their methods for analysis, application of data science on their data 2. Research all smart bins that are available Companies, survey paper, scientific papers etc. – if and how they identify food, if and how measure food loss and food waste and what type of data they collect, prices of their bins(as they affect the sales and hence, implementations) 3. Contact IKEA, Four Seasons etc as they teamed up with Winnow. IKEA may have their own data. | As we are targetting on getting the first survey paper done by end of August, we are focusing on whats there in the domain of food waste management systems and smart bins currently in the market. |  | 1. Contacted few of Winnow's clients and waiting for their responses. 2. Scheduled a meeting with Winnow. 3. Researched on some smart bins which will help us analyze and design our smart bin. 4. Analyzed Kitro as well.
5 | 1st Aug Week | 1. Curate list of questions to ask Winnow. 2. Get the clients questionnaire verified by Professor. 3. Reach out to rest of the clients of Winnow to know their perspective and if there are any gaps that Winnow bin is not filling. 5. Make slides to present on Wednesday 4. Meeting with Winnow. |  |  | 1. Curated list of questions to ask Winnow. 2. Got the clients questionnaire verified by Professor. 3. Reached out to rest of the clients of Winnow to know their perspective and if there are any gaps that Winnow bin is not filling. 5. Made slides to present on Wednesday 4. Meeting with Winnow.
6 | 7th Aug Week | 1. Draft the slides to be presented on Wednesday and get it reviewed. -- Add to it the themes of both papers. -- 1st paper - whats going on in industry, info gained from Winnow, focus on Winnow.